Request for Proposal (RFP 24 /2012)

Date: 29.06.2012

Dear Sir/Madam,

Subject: RFP24/2012 - Community Outreach Programme for Introducing Agricultural Waste Management System in the Prespa Region

- The United Nations Development Programme (UNDP) invites local NGO’s to submit a proposal in MKD, VAT exempted for delivery of Community Outreach Programme for Introducing Agricultural Waste Management System in the Prespa Region, as per the Terms of Reference (TOR).

- To enable you to submit a proposal, attached are:

- Instructions to Offerors …………… . (Annex I)

- Terms of Reference (TOR)………… .(Annex II)

- Proposal Submission Form …………..(Annex III)

- General Conditions of Contract……. .(Annex IV)

- Your offer comprising of technical proposal and financial proposal, in separate sealed envelopes, should reach the following address no later than 13 July 2012 by 14:30 h.

UNDP

RFP 24/2012 for Community Outreach Programme for Introducing Agricultural Waste Management System in the Prespa Region

Address: 8ma Udarna Brigada 2

1000 Skopje

- If you request additional information, we would endeavor to provide information expeditiously, but any delay in providing such information will not be considered a reason for extending the submission date of your proposal.

- You are requested to acknowledge receipt of this letter and to indicate whether or not you intend to submit a proposal at the following e-mail address: procurement.mk@undp.org

###### Annex I

###### Instructions to Offerors

# Introduction

- General: procurement method used: Request for Proposal (RFP)

- Cost of proposal

The Offeror shall bear all costs associated with the preparation and submission of the Proposal, the UNDP will in no case be responsible or liable for those costs, regardless of the conduct or outcome of the solicitation.

# Solicitation Documents

- Contents of solicitation documents

Proposals must offer services for the total requirement. Proposals offering only part of the requirement will be rejected. The Offeror is expected to examine all corresponding instructions, forms, terms and specifications contained in the Solicitation Documents. Failure to comply with these documents will be at the Offeror’s risk and may affect the evaluation of the Proposal.

- Clarification of solicitation documents

A prospective Offeror requiring any clarification of the Solicitation Documents may notify the procuring UNDP entity in writing at the organization’s mailing address procurement.mk@undp.org. Written copies of the organization’s response (including an explanation of the query but without identifying the source of inquiry) will be sent to all prospective Offerors and will be posted on UNDP web site www.undp.org.mk (Q&A ref. RFP 24/2012)

- Amendments of solicitation documents

At any time prior to the deadline for submission of Proposals, the procuring UNDP entity may, for any reason, whether at its own initiative or in response to a clarification requested by a prospective Offeror, modify the Solicitation Documents by amendment.

Any amendment will be posted at UNDP web site

In order to afford prospective Offerors reasonable time in which to take the amendments into account in preparing their offers, the procuring UNDP entity may, at its discretion, extend the deadline for the submission of Proposals.

# Preparation of Proposals

- Language of the proposal

The Proposals prepared by the Offeror and all correspondence and documents relating to the Proposal exchanged by the Offeror and the procuring UNDP entity shall be written in the English language.

- Documents comprising the proposal

The Proposal shall comprise the following components:

- Proposal submission form;

- Technical part of the Proposal, including documentation to demonstrate that the Offeror meets all requirements; (

- Price proposal shall only be submitted in a hard copy in a sealed envelope and  presented around deliverables and each deliverable shall have detailed budget break down

- Proposal form

The Offeror shall structure the operational and technical part of its Proposal as follows:

- NGO profile/experience

- Methodology and work plan

- Reference list of similar assignments

- Qualifications and experience of the proposed team.

- Proposal prices

The price proposal shall be presented per deliverables and each deliverable shall have detailed budget break down

- Proposal currencies

All prices shall be quoted in MKD, VAT exempted.

- Period of validity of proposals

Proposals shall remain valid for hundred twenty (120) days after the date of Proposal submission prescribed by the procuring UNDP entity, pursuant to the deadline clause. A Proposal valid for a shorter period may be rejected by the procuring UNDP entity on the grounds that it is non-responsive.

In exceptional circumstances, the procuring UNDP entity may solicit the Offeror’s consent to an extension of the period of validity. The request and the responses thereto shall be made in writing. An Offeror granting the request will not be required nor permitted to modify its Proposal.

- Format and signing of proposals

A Proposal shall contain no interlineations, erasures, or overwriting except, as necessary to correct errors made by the Offeror, in which case such corrections shall be initialed by the person or persons signing the Proposal.

- Payment

UNDP shall effect payments to the Contractor after acceptance by UNDP of the invoices submitted by the contractor, upon achievement of the corresponding milestones.

### Submission of Proposals

- Sealing and marking of proposals

The Offeror shall seal the Proposal in one outer and two inner envelopes, as detailed below.

- The outer envelope shall be:

- addressed to

UNDP

for Community Outreach Programme for Introducing Agricultural Waste Management System in the Prespa Region

Address: 8ma Udarna Brigada 2

1000 Skopje

- Both inner envelopes shall indicate the name and address of the Offeror. The first inner envelope shall contain the information specified in Clause 8 (Proposal form) above. The second inner envelope shall include the price schedule duly identified as such.

Note, if the inner envelopes are not sealed and marked as per the instructions in this clause, the procuring UNDP entity will not assume responsibility for the Proposal’s misplacement or premature opening.

- Deadline for submission of proposals

Proposals must be received by the procuring UNDP entity at the address specified under clause Sealing and marking of Proposals no later than 13 July 2012 by 14:30 h.

The procuring UNDP entity may, at its own discretion extend this deadline for the submission of Proposals by amending the solicitation documents in accordance with clause Amendments of Solicitation Documents, in which case all rights and obligations of the procuring UNDP entity and Offerors previously subject to the deadline will thereafter be subject to the deadline as extended.

- Late Proposals

Any Proposal received by the procuring UNDP entity after the deadline for submission of proposals, pursuant to clause Deadline for the submission of proposals, will be rejected.

# Modification and withdrawal of Proposals

The Offeror may withdraw its Proposal after the Proposal’s submission, provided that written notice of the withdrawal is received by the procuring UNDP entity prior to the deadline prescribed for submission of Proposals.

The Offeror’s withdrawal notice shall be prepared, sealed, marked, and dispatched in accordance with the provisions of clause Deadline for Submission of Proposals. The withdrawal notice may also be sent by telex or fax but followed by a signed confirmation copy.

No Proposal may be modified subsequent to the deadline for submission of proposals.

No Proposal may be withdrawn in the Interval between the deadline for submission of proposals and the expiration of the period of proposal validity specified by the Offeror on the Proposal Submission Form.

# Opening and Evaluation of Proposals

- Opening of proposals

The procuring entity will open the Proposals in the presence of an Evaluation Committee.

- Clarification of proposals

To assist in the examination, evaluation and comparison of Proposals, the Purchaser may at its discretion, ask the Offeror for clarification of its Proposal. The request for clarification and the response shall be in writing and no change in price or substance of the Proposal shall be sought, offered or permitted.

- Preliminary examination

The Purchaser will examine the Proposals to determine whether they are complete, whether any computational errors have been made, whether the documents have been properly signed, and whether the Proposals are generally in order.

Prior to the detailed evaluation, the Purchaser will determine the substantial responsiveness of each Proposal to the Request for Proposals (RFP). For purposes of these Clauses, a substantially responsive Proposal is one which conforms to all the terms and conditions of the RFP without material deviations. The Purchaser’s determination of a Proposal’s responsiveness is based on the contents of the Proposal itself without recourse to extrinsic evidence.

A Proposal determined as not substantially responsive will be rejected by the Purchaser and may not subsequently be made responsive by the Offeror by correction of the non-conformity.

- Evaluation and comparison of proposals-cumulative method

A two-stage procedure is utilized in evaluating the proposals, with evaluation of the technical proposal being completed prior to any price proposal being opened and compared.  The price proposal of the Proposals will be opened only for submissions that passed the minimum technical score of 70% or 490 points of the obtainable score of 700 points in the evaluation of the technical proposals.

The technical proposal is evaluated on the basis of its responsiveness to the Term of Reference (TOR).

The offer with the lowest price will receive the total 300 points. Other offers with higher prices will receive their respective scores according the following formula:

Lowest Bid

300     ×

Proposed Bid

The Applicant/s will be awarded a contract with the highest aggregate score based on technical and financial proposal.

Arithmetical errors will be rectified on the following basis: If there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected. If the Offeror does not accept the correction of errors, its Proposal will be rejected. If there is a discrepancy between words and figures the amount in words will prevail.

#### Technical Evaluation Criteria

| Summary of Technical Proposal Evaluation Forms |  | Score Weight | Points Obtainable |
| --- | --- | --- | --- |
| 1. | Experience/Expertise of the service provider (NGO) submitting Proposal | 21,43% | 150 |
| 2. | Proposed Methodology including Work Plan | 35,71% | 250 |
| 3. | Personnel | 42,86% | 300 |
|  | Total |  | 700 |

The obtainable number of points specified for each evaluation criterion which indicates the relative significance or weight of the item in the overall evaluation process is given below:

| - The NGO/Applicant: |  | max points: 400 |
| --- | --- | --- |
| Criteria A: Reference list of similar assignments, and evidence of at least three (3) assignments of a nature and complexity comparable to this assignment |  | max points: 150 |
| 1. | Min. two (3) similar assignments completed | 100 points |
| 2. | Three (4) to five (6) similar assignments completed | 120 points |
| 3. | More than 7 similar assignments | 150 points |
| Total Criteria A: |  | _________ points |
| Criteria B: Brief methodology and approach on how the assignment will be carried out |  | max points: 250 |
| B1. | To what degree the task is understood | Max. 50 points |
| B2. | Have the important aspects of the task been addressed in sufficient detail? | Max. 80 points |
| B3. | Is the presentation of the methodology clear and is the sequence of activities and the planning logical, realistic and promise efficient implementation to the project. | Max. 120 points |
| Total Criteria B: |  | _________ points |
| Technical Criteria of NGO/Applicant of total evaluation: Total of Criteria A + Criteria B : |  | Max. 400 points |
| - Team Leader: |  | max points: 200 |
| Criteria A: Education |  | max points: 40 |
| 1. | University degree in marketing, communication or similar | 20 points |
| 2. | MSc degree in marketing, communication or similar | 30 points |
| 3. | PhD in in marketing, communication or similar | 40 points |
| Total Criteria A: |  | _________ points |
| Criteria B: Professional Experience |  | max points: 50 |
| 1. | Min. two (2) similar assignments as a Team Leader | 30 points |
| 2. | Three (3) to five (5) similar assignments as a Team Leader | 40 points |
| 3. | More than 6 similar assignments as a Team Leader | 50 points |
| Total Criteria B: |  | _________ points |
| Criteria C: Professional experience: at least 5 years of professional experience in conducting and analyzing surveys, conducting promotion campaigns, experience in statistical modeling, marketing, public relations or similar |  | max points: 50 |
| 1. | At least 5years of professional experience | 30 points |
| 2. | More than 5 and less than 8 years of professional experience | 40 points |
| 3. | More than 8 years of professional experience | 50 points |
|  |  | max points: 60 |
| Total Criteria D: |  | _________ points |
| Technical Criteria of Team Leader of NGO/Applicant of total evaluation: Total of Criteria A + Criteria B + Criteria C+ Criteria D: |  | Max. 200 points |
| - Communication Expert: |  | max points: 100 |
| Criteria A: Education |  | max points: 20 |
| 1. | University degree in marketing, communication or similar | 10 points |
| 2. | MSc degree in in marketing, communication or similar | 15 points |
| 3. | PhD in marketing, communication or similar | 20 points |
| Total Criteria A: |  | _________ points |
| Criteria B: Professional Experience |  | max points: 30 |
| 1. | Min. two (2) similar assignments completed | 20 points |
| 2. | Three (3) to five (5) similar assignments completed | 25 points |
| 3. | More than 6 similar assignments completed | 30 points |
| Total Criteria B: |  | _________ points |
| Criteria C: Professional experience: at least 3 years of professional experience in conducting and analysing surveys, conducting promotion campaigns, experience in statistical modelling, marketing, public relations |  | max points: 50 |
| 1. | At least 3 years of professional experience | 30 points |
| 2. | More than 3and less than 8 years of professional experience | 40 points |
| 3. | More than 8 years of professional experience | 50 points |
| Total Criteria D: |  | _________ points |
| Technical Criteria of the Communication Expert of the NGO/Applicant of total evaluation: Total of Criteria A + Criteria B + Criteria C: |  | Max. 100 points |

The obtainable number of points specified for each evaluation criterion which indicates the relative significance or weight of the item in the overall evaluation process is given in Annex 2 – Terms of Reference.

### Award of Contract

- Award criteria, award of contract

The procuring UNDP entity reserves the right to accept or reject any Proposal, and to annul the solicitation process and reject all Proposals at any time prior to award of contract, without thereby incurring any liability to the affected Offeror or any obligation to inform the affected Offeror or Offerors of the grounds for the Purchaser’s action

Prior to expiration of the period of proposal validity, the procuring UNDP entity will award the contract to the qualified Offeror whose Proposal after being evaluated is considered to be the most responsive to the needs of the organisation and activity concerned.

- Purchaser’s right to vary requirements at time of award

The Purchaser reserves the right at the time of award of contract to vary the quantity of services and goods specified in the RFP without any change in price or other terms and conditions.

- Signing of the contract

Within 7 days of receipt of the contract the successful Offeror shall sign and date the contract and return it to the Purchaser.

- Performance security

n/a

26. Vendor protest

Our vendor protest procedure is intended to afford an opportunity to appeal to persons or firms not awarded a purchase order or contract in a competitive procurement process. It is not available to non-responsive or non-timely proposers/bidders or when all proposals/bids are rejected. In the event that you believe you have not been fairly treated, you can find detailed information about vendor protest procedures in the following link: http://www.undp.org/procurement/protest.shtml.

Annex 2

- Terms of Reference

| Job Title: | Community Outreach Programme for Introducing Agricultural Waste Management System in the Prespa Region |
| --- | --- |
| Project: | 00077357 - Pilot Project for Biodegradable Waste Management in Prespa Region |
| Duty Station: | Resen |
| Expected Duration of Assignment: | 6 months (July – December 2012) |
| Expected Starting date: | 20 July 2012 |
| Expected End of the Assignment: | 20 December 2012 |

- Background

Agriculture plays a significant role in the Prespa region in terms of employment and economic sustainability. Over 60% of the local population in Resen and the surrounding villages depends on agricultural activities, mainly apple production.

According to the “Feasibility Study on Biodegradable Waste Management in the Prespa Region” commissioned by UNDP in 2010 and the study for piloting biodegradable waste management - “Pilot Composting Plant in Resen”, the annual apple production ranges from 80,000 to 110,000 tons, but in some years, due to low market demands, more than 10,000 tons are discarded as waste.

Due to low environmental awareness of the local population, and the lack of a management solution in place, an extraordinary amount of biodegradable waste is currently being illegally disposed/dumped either in Prespa Lake, or along the Golema Reka river corridors, local roads, bridges, or in illegal dump sites at the villages (mostly rotten apple ranging from 7 - 12% of the total production).

The studies offered management solution by establishing a pilot central composting plant and a number of collection stations, as a viable management solution for the biodegradable waste generated around the town of Resen and the village of Jankovec. The objective of this system is to substantially reduce the large amount of organic waste currently being discarded in the Prespa Lake Basin, transforming the biodegradable waste into products of intrinsic value - compost.

Currently, there are on-going construction works for the establishment of a new system for biodegradable waste management, a completion of which is expected in late October 2012.

This system complements the Pesticide Packaging Waste Management System developed over the past years, thanks to the UNDP’s ‘Restoration of Golema Reka’ project and the GEF Small Grants Programme. Support has been provided to the local community for safe and controlled collection and disposal of one of the most harmful wastes associated with agricultural activity in the region.

Both systems are (to be) managed by the Public Communal Enterprise “Proleter” in Resen.

In order to facilitate the operationalization and management of both systems, as well as, to ensure that all relevant target audiences, understand and are aware of the benefits of using the solid waste management systems in the selected region of Prespa UNDP is seeking for a NGO which will develop and conduct a tailored community outreach programme.

- Objectives

The main objective of the assignment is to developed and implement six months targeted community outreach programme in the Prespa region that will ultimately contribute to decreased human pressure on the Prespa watershed. The task shell be carried out in two phases which should be mindful of the seasonal aspects of annual waste generation cycles. While the major quantities of pesticide packaging are mainly generated in the period April – September, the waste apples are generated from December, with the peak around March – May.

Phase I:

- To develop educational materials for the local population and farmers in particular, on the importance and benefits of using the established pesticide packaging waste management system;

- To ensure wide distribution of these materials through a variety of communications tools;

Phase II:

- To develop educational materials for the local population and farmers in particular, on the importance and benefits of using the biodegradable waste management system (currenty under development) and the benefits of using compost;

- To ensure wide distribution of these materials through a variety of communications tools;

- To produce an impact assessment of the conducted outreach programme (based on success indicators agreed from the very beginning in consultation with the Project Manager and the Communications Officer)

- Tasks (Scope of Work)

Under the supervision of the Project Manager and in collaboration with the Union of Agricultural Producers, the municipal authorities, the Public Entreprise and the Natural Capital Resource Center, the NGO will be responsible for the following tasks:

Task 1: Review the UNDP Feasibility Waste Management Study for Prespa Region

- Review and analyse the relevant chapters of the Feasibility Waste Management Study for Prespa Region and get acquainted with the guidelines and parameters for Biodegradable Waste System planning.

Task 2: Review the UNDP - Biodegradable Waste Management in the Prespa Region - Pilot Composting Project

- Review and analyse all the relevant chapters of the Biodegradable Waste Management in the Prespa Region - Pilot Composting Project with an aim to get acquainted with the designed management system and projected quantities of the final product - compost to be produced in the Composting Plant developed under the Pilot Project;

- Get acquainted in detail with the pattern for collection and transport of the waste under the Pilot project;

- Review the detailed scheme of the Pilot Composting Plant and get acquainted with the composting process.

Task 3: Review the UNDP - “Guidelines for handling of pesticide packaging”, a study prepared under the Project “Integrated Ecosystem Management in the Prespa Lakes Basin”

Task 4: Based on the review of the available studies and previous introduction by the project management, and following a series of discussions with Union of Agricultural Producers, municipality officials, and the representatives/management of the public communal enterprise “Proleter”, the NGO shall:

- develop educational materials for the local population and farmers in particular, on the importance and benefits of using the established pesticide packaging waste management system;

- develop educational materials for the local population and farmers in particular, on the importance and benefits of using the biodegradable waste management system;

- propose best communication tools and channels for reaching out to target audiences (having in mind that there is no local tv, radio);

- ensure wide distribution of these materials through a variety of communications tools;

- propose impact & success indicators for monitoring progress in the establishment of both waste management systems;

- organize several stakeholder events (workshops, presentations, meetings) in the Municipality of Resen and the local communities in the geographical scope of the waste collection sites (both pesticide packaging and biodegradable waste); support in conducting the community involvement will be provided by the Natural Capital Resource Center (two staff to be made available).

- Qualification and Experience

- Applicant’s/NGO’s requirements (mandatory):

- NGO/CSO registered in accordance with the applicable national legislature;

- Previous experiance in carrying out similar assignments. Evidence of at least 3 assignments in nature and complexity

- Qualification of the proposed personnel

  - Team Leader

- University degree in marketing, communication or similar. Advanced degree shall be considered as an asset Professional experience:  at least 5 years  of professional experience in conducting and analysing surveys, conducting promotion campaigns, experience in statistical modelling, marketing, public relations;

- Evidence of performing at least two similar assignments  as a Team Leader;

  - Communication expert

- University degree in marketing, communication or similar. . Advanced degree shall be considered as an asset at least 3 years  of professional experience in conducting and analysing surveys, conducting promotion campaigns, experience in statistical modelling, marketing, public relations;

- Evidence of performing at least two similar assignments;

- Reporting

The NGO shall report to UNDP through the Team Leader. The NGO shall provide monthly and final reports. Developed plans and materials shall be approved by Project Manager prior to implementation.

- Duration of assignment

The total duration of the assignment is six months.

- Phase one (July/September): 3 (three) months for developing and implementation of the promotion of the pesticide packaging waste management system;

- Phase two (October/December): additional 3 (three) months  for developing and implementation of a promotion campaign and introducing the biodegradable waste management system to the identified beneficiaries in the target region and to measure the feedback from the promotion campaign from phase (I);

- Deliverables

Phase I:

- A draft proposal delivered to UNDP for approval 30 days after signing the contract, consisting of a design of educational materials to be delivered to the local population and farmers on the importance and benefits of using the established pesticide packaging waste.This report shall propose best communication tools and channels for reaching out to target audiences and shall propose impact & success indicators for monitoring progress in the establishment of pesticide packaging waste management system.

- Organize 2 (two) stakeholder events (workshops, presentations, meetings) in the Municipality of Resen and the local communities.

- Produce monthly reports (the first monthly report is due on 30 September 2012 and the second one is due on 31 October 2012) on progress of the outreach programme in the establishment of pesticide packaging waste management system, based on the impact & success indicators approved by UNDP.

Phase II:

- Develop a draft proposal delivered to UNDP for approval on 15 October 2012   consisting of a design of educational materials to be delivered to the local population and farmers on the importance and benefits of using the biodegradable waste management system in development. This report shall propose best communication tools and channels for reaching out to target audiences and shall propose impact & success indicators for monitoring progress in the establishment of biodegradable waste management system.

- Organize 2 (two) stakeholder events during this phase  (workshops, presentations, meetings) in the Municipality of Resen and the local communities, in particular - introducing the compost to the identified target market as a substitute to commonly used fertilizers.

- Deliver the third monthly report due on 30 November 2012  on progress of the outreach programme in the establishment of the biodegradable waste management system, based on the impact & success indicators approved by UNDP.

- Final report due on 20 December 2012 on progress of the outreach programme in the establishment of both waste management systems, based on the approved indicators. The final report shall include a feedback analysis of the conducted promotion activities conveying the massage to the beneficiaries, towards designing the required level of services for of both waste management systems.

- Payment Schedule

  - First instalment: 20% upon receipt and approval of the draft proposal on educational materials and communication tools/channels for reaching out to target audiences on the importance and benefits of using the established pesticide packaging waste (Phase I);

  - Second instalment: 10% upon receipt and approval of the first monthly report (Phase I);

  - Third instalment: 10% upon receipt and approval of the second monthly report (Phase I);

  - Fourth instalment: 20% upon receipt and approval of the draft proposal on educational materials and communication tools/channels for reaching out to target audiences on the importance and benefits of using the biodegradable waste management system in development and compost as substitute of fertilizers (Phase II);

  - Fifth instalment: 10% upon receipt and approval of the third monthly report (Phase II);

  - Sixth instalment: 30% upon receipt and approval of the Final report (Phase II).

- Application procedure

  - Technical proposal: The NGO/Applicant is expected to provide the following documentation (mandatory):

- Copies of original documents defining the constitution or legal status, place of registration, and principal place of operation of the NGO;

- NGO profile (short description of previous experience);

- Reference list of similar assignments, and evidence of at least three (3) assignments of a nature and complexity comparable to this requirement and values of the contracts expressed in MKD (including name/contact details of clients who can be contacted for reference).

- Qualifications and experience of the Team Leader and the Communication Expert who shall have relevant professional and technical capacity and appropriate experience in execution similar tasks (see Technical Evaluation Criteria);

- Proposed methodology and approach for conducting (i) Research providing first-hand information about the immediate beneficiaries,including a/ problem definition and research objectives; b/ research plan for collecting information, c/ Implementing the research plan and d/ Interpreting and recording the research findings (ii) Promotion campaign (iii) New-product (compost) introduction in the first phase of the activities and (iv) Feedback analysis of the conducted promotion activities in the second phase of the activities

  - Financial offer  as a lump sum (including all costs for the missions and the home based desk work such as consultancy fee, travel costs, daily subsistence allowance etc.)

**** The price proposal shall be presented per deliverables and each deliverable shall have detailed budget break down

- Evaluation Method - Cumulative Scoring

#### Technical Evaluation Criteria

| Summary of Technical Proposal Evaluation Forms |  | Score Weight | Points Obtainable |
| --- | --- | --- | --- |
| 1. | Experience/Expertise of the service provider (NGO) submitting Proposal | 21,43% | 150 |
| 2. | Proposed Methodology including Work Plan | 35,71% | 250 |
| 3. | Personnel | 42,86% | 300 |
|  | Total |  | 700 |

The obtainable number of points specified for each evaluation criterion which indicates the relative significance or weight of the item in the overall evaluation process is given below:

| - The NGO/Applicant: |  | max points: 400 |
| --- | --- | --- |
| Criteria A: Reference list of similar assignments, and evidence of at least three (3) assignments of a nature and complexity comparable to this assignment |  | max points: 150 |
| 1. | Min. two (3) similar assignments completed | 100 points |
| 2. | Three (4) to five (6) similar assignments completed | 120 points |
| 3. | More than 7 similar assignments | 150 points |
| Total Criteria A: |  | _________ points |
| Criteria B: Brief methodology and approach on how the assignment will be carried out |  | max points: 250 |
| B1. | To what degree the task is understood | Max. 50 points |
| B2. | Have the important aspects of the task been addressed in sufficient detail? | Max. 80 points |
| B3. | Is the presentation of the methodology clear and is the sequence of activities and the planning logical, realistic and promise efficient implementation to the project. | Max. 120 points |
| Total Criteria B: |  | _________ points |
| Technical Criteria of NGO/Applicant of total evaluation: Total of Criteria A + Criteria B : |  | Max. 400 points |
| - Team Leader: |  | max points: 200 |
| Criteria A: Education |  | max points: 40 |
| 1. | University degree in marketing, communication or similar | 20 points |
| 2. | MSc degree in marketing, communication or similar | 30 points |
| 3. | PhD in in marketing, communication or similar | 40 points |
| Total Criteria A: |  | _________ points |
| Criteria B: Professional Experience |  | max points: 50 |
| 1. | Min. two (2) similar assignments as a Team Leader | 30 points |
| 2. | Three (3) to five (5) similar assignments as a Team Leader | 40 points |
| 3. | More than 6 similar assignments as a Team Leader | 50 points |
| Total Criteria B: |  | _________ points |
| Criteria C: Professional experience: at least 5 years of professional experience in conducting and analyzing surveys, conducting promotion campaigns, experience in statistical modeling, marketing, public relations or similar |  | max points: 50 |
| 1. | At least 5years of professional experience | 30 points |
| 2. | More than 5 and less than 8 years of professional experience | 40 points |
| 3. | More than 8 years of professional experience | 50 points |
|  |  | max points: 60 |
| Total Criteria D: |  | _________ points |
| Technical Criteria of Team Leader of NGO/Applicant of total evaluation: Total of Criteria A + Criteria B + Criteria C+ Criteria D: |  | Max. 200 points |
| - Communication Expert: |  | max points: 100 |
| Criteria A: Education |  | max points: 20 |
| 1. | University degree in marketing, communication or similar | 10 points |
| 2. | MSc degree in in marketing, communication or similar | 15 points |
| 3. | PhD in marketing, communication or similar | 20 points |
| Total Criteria A: |  | _________ points |
| Criteria B: Professional Experience |  | max points: 30 |
| 1. | Min. two (2) similar assignments completed | 20 points |
| 2. | Three (3) to five (5) similar assignments completed | 25 points |
| 3. | More than 6 similar assignments completed | 30 points |
| Total Criteria B: |  | _________ points |
| Criteria C: Professional experience: at least 3 years of professional experience in conducting and analysing surveys, conducting promotion campaigns, experience in statistical modelling, marketing, public relations |  | max points: 50 |
| 1. | At least 3 years of professional experience | 30 points |
| 2. | More than 3and less than 8 years of professional experience | 40 points |
| 3. | More than 8 years of professional experience | 50 points |
| Total Criteria D: |  | _________ points |
| Technical Criteria of the Communication Expert of the NGO/Applicant of total evaluation: Total of Criteria A + Criteria B + Criteria C: |  | Max. 100 points |

Annex III

PROPOSAL SUBMISSION FORM

Dear Sir / Madam,

Having examined the Solicitation Documents, the receipt of which is hereby duly acknowledged, we, the undersigned, offer to deliver a Community Outreach Programme for Introducing Agricultural Waste Management System in the Prespa Region ref. IFP ___ / 2012 for the sum as may be ascertained in accordance with the Price Schedule attached herewith and made part of this Proposal.

We undertake, if our Proposal is accepted, to commence and complete delivery of all services specified in the contract within the time frame stipulated.

We agree to abide by this Proposal for a period of 120 days from the date fixed for opening of

Proposals in the Invitation for Proposal, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

We understand that you are not bound to accept any Proposal you may receive.

Dated this day /month 	……………………… of year…………..

### Signature

(In the capacity of)

Duly authorised to sign Proposal for and on behalf of:…………………………………………..

Annex IV

## General Conditions for Professional Services

- LEGAL STATUS

The Contractor shall be considered as having the legal status of an independent contractor vis-à-vis UNDP. The Contractor's personnel and sub-contractors shall not be considered in any respect as being the employees or agents of UNDP or the United Nations.

- SOURCE OF INSTRUCTIONS

The Contractor shall neither seek nor accept instructions from any authority external to UNDP in connection with the performance of its services under this Contract. The Contractor shall refrain from any action which may adversely affect UNDP or the United Nations and shall fulfil its commitments with the fullest regard to the interests of UNDP.

- CONTRACTOR'S RESPONSIBILITY FOR EMPLOYEES

The Contractor shall be responsible for the professional and technical competence of its employees and will select, for work under this Contract, reliable individuals who will perform effectively in the implementation of this Contract, respect the local customs, and conform to a high standard of moral and ethical conduct.

- ASSIGNMENT

The Contractor shall not assign, transfer, pledge or make other disposition of this Contract or any part thereof, or any of the Contractor's rights, claims or obligations under this Contract except with the prior written consent of UNDP.

- SUB-CONTRACTING

In the event the Contractor requires the services of sub-contractors, the Contractor shall obtain the prior written approval and clearance of UNDP for all sub-contractors. The approval of UNDP of a sub-contractor shall not relieve the Contractor of any of its obligations under this Contract. The terms of any sub-contract shall be subject to and conform with the provisions of this Contract.

- OFFICIALS NOT TO BENEFIT

The Contractor warrants that no official of UNDP or the United Nations has received or will be offered by the Contractor any direct or indirect benefit arising from this Contract or the award thereof. The Contractor agrees that breach of this provision is a breach of an essential term of this Contract.

- INDEMNIFICATION

The Contractor shall indemnify, hold and save harmless, and defend, at its own expense, UNDP, its officials, agents, servants and employees from and against all suits, claims, demands, and liability of any nature or kind, including their costs and expenses, arising out of acts or omissions of the Contractor, or the Contractor's employees, officers, agents or sub-contractors, in the performance of this Contract. This provision shall extend, inter alia, to claims and liability in the nature of workmen's compensation, products liability and liability arising out of the use of patented inventions or devices, copyrighted material or other intellectual property by the Contractor, its employees, officers, agents, servants or sub-contractors. The obligations under this Article do not lapse upon termination of this Contract.

- INSURANCE AND LIABILITIES TO THIRD PARTIES

  - The Contractor shall provide and thereafter maintain insurance against all risks in respect of its property and any equipment used for the execution of this Contract.

  - The Contractor shall provide and thereafter maintain all appropriate workmen's compensation insurance, or its equivalent, with respect to its employees to cover claims for personal injury or death in connection with this Contract.

  - The Contractor shall also provide and thereafter maintain liability insurance in an adequate amount to cover third party claims for death or bodily injury, or loss of or damage to property, arising from or in connection with the provision of services under this Contract or the operation of any vehicles, boats, airplanes or other equipment owned or leased by the Contractor or its agents, servants, employees or sub-contractors performing work or services in connection with this Contract.

  - Except for the workmen's compensation insurance, the insurance policies under this Article shall:

- Name UNDP as additional insured;

- Include a waiver of subrogation of the Contractor's rights to the insurance carrier against UNDP;

- Provide that UNDP shall receive thirty (30) days written notice from the insurers prior to any cancellation or change of coverage.

  - The Contractor shall, upon request, provide UNDP with satisfactory evidence of

the insurance required under this Article.

### 9.   ENCUMBRANCES/LIENS

The Contractor shall not cause or permit any lien, attachment or other encumbrance by any person to be placed on file or to remain on file in any public office or on file with UNDP against any monies due or to become due for any work done or materials furnished under this Contract, or by reason of any other claim or demand against the Contractor.

10.  TITLE TO EQUIPMENT

Title to any equipment and supplies that may be furnished by UNDP shall rest with UNDP and any such equipment shall be returned to UNDP at the conclusion of this Contract or when no longer needed by the Contractor. Such equipment, when returned to UNDP, shall be in the same condition as when delivered to the Contractor, subject to normal wear and tear. The Contractor shall be liable to compensate UNDP for equipment determined to be damaged or degraded beyond normal wear and tear.

- COPYRIGHT, PATENTS AND OTHER PROPRIETARY RIGHTS

UNDP shall be entitled to all intellectual property and other proprietary rights including but not limited to patents, copyrights, and trademarks, with regard to products, or documents and other materials which bear a direct relation to or are produced or prepared or collected in consequence of or in the course of the execution of this Contract. At the UNDP's request, the Contractor shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring them to UNDP in compliance with the requirements of the applicable law.

12.  USE OF NAME, EMBLEM OR OFFICIAL SEAL OF UNDP OR THE UNITED NATIONS

The Contractor shall not advertise or otherwise make public the fact that it is a Contractor with UNDP, nor shall the Contractor, in any manner whatsoever use the name, emblem or official seal of UNDP or the United Nations, or any abbreviation of the name of UNDP or the United Nations in connection with its business or otherwise.

13.  CONFIDENTIAL NATURE OF DOCUMENTS AND INFORMATION

  - All maps, drawings, photographs, mosaics, plans, reports, recommendations, estimates, documents and all other data compiled by or received by the Contractor under this Contract shall be the property of UNDP, shall be treated as confidential and shall be delivered only to UNDP authorized officials on completion of work under this Contract.

  - The Contractor may not communicate at any time to any other person, Government or authority external to UNDP, any information known to it by reason of its association with UNDP which has not been made public except with the authorization of UNDP; nor shall the Contractor at any time use such information to private advantage. These obligations do not lapse upon termination of this Contract.

14. FORCE MAJEURE; OTHER CHANGES IN CONDITIONS

  - Force majeure, as used in this Article, means acts of God, war (whether declared or not), invasion, revolution, insurrection, or other acts of a similar nature or force which are beyond the control of the Parties.

  - In the event of and as soon as possible after the occurrence of any cause constituting force majeure, the Contractor shall give notice and full particulars in writing to UNDP, of such occurrence or change if the Contractor is thereby rendered unable, wholly or in part, to perform its obligations and meet its responsibilities under this Contract. The Contractor shall also notify UNDP of any other changes in conditions or the occurrence of any event which interferes or threatens to interfere with its performance of this Contract. The notice shall include steps proposed by the Contractor to be taken including any reasonable alternative means for performance that is not prevented by force majeure. On receipt of the notice required under this Article, UNDP shall take such action as, in its sole discretion, it considers to be appropriate or necessary in the circumstances, including the granting to the Contractor of a reasonable extension of time in which to perform its obligations under this Contract.

  - If the Contractor is rendered permanently unable, wholly, or in part, by reason of force majeure to perform its obligations and meet its responsibilities under this Contract, UNDP shall have the right to suspend or terminate this Contract on the same terms and conditions as are provided for in Article 15, "Termination", except that the period of notice shall be seven (7) days instead of thirty (30) days.

15. TERMINATION

  - Either party may terminate this Contract for cause, in whole or in part, upon thirty days notice, in writing, to the other party. The initiation of arbitral proceedings in accordance with Article 16 "Settlement of Disputes" below shall not be deemed a termination of this Contract.

  - UNDP reserves the right to terminate without cause this Contract at any time upon 15 days prior written notice to the Contractor, in which case UNDP shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination.

  - In the event of any termination by UNDP under this Article, no payment shall be due from UNDP to the Contractor except for work and services satisfactorily performed in conformity with the express terms of this Contract. The Contractor shall take immediate steps to terminate the work and services in a prompt and orderly manner and to minimize losses and further expenditures.

  - Should the Contractor be adjudged bankrupt, or be liquidated or become insolvent, or should the Contractor make an assignment for the benefit of its creditors, or should a Receiver be appointed on account of the insolvency  of the Contractor, UNDP may, without prejudice to any other right or remedy it may have, terminate this Contract forthwith. The Contractor shall immediately inform UNDP of the occurrence of any of the above events.

- SETTLEMENT OF DISPUTES

  - Amicable Settlement

The Parties shall use their best efforts to settle amicably any dispute, controversy or claim arising out of, or relating to this Contract or the breach, termination or invalidity thereof. Where the parties wish to seek such an amicable settlement through conciliation, the conciliation shall take place in accordance with the UNCITRAL Conciliation Rules then obtaining, or according to such other procedure as may be agreed between the parties.

  - Arbitration

Unless, any such dispute, controversy or claim between the Parties arising out of or relating to this Contract or the breach, termination or invalidity thereof is settled amicably under the preceding paragraph of this Article within sixty (60) days after receipt by one Party of the other Party's request for such amicable settlement, such dispute, controversy or claim shall be referred by either Party to arbitration in accordance with the UNCITRAL Arbitration Rules then obtaining, including its provisions on applicable law. The arbitral tribunal shall have no authority to award punitive damages. The Parties shall be bound by any arbitration award rendered as a result of such arbitration as the final adjudication of any such controversy, claim or dispute.

- PRIVILEGES AND IMMUNITIES

Nothing in or relating to this Contract shall be deemed a waiver, express or implied, of any of the privileges and immunities of the United Nations, including its subsidiary organs.

- TAX EXEMPTION

  - Section 7 of the Convention on the Privileges and Immunities of the United Nations provides, inter-alia, that the United Nations, including its subsidiary organs, is exempt from all direct taxes, except charges for public utility services, and is exempt from customs duties and charges of a similar nature in respect of articles imported or exported for its official use. In the event any governmental authority refuses to recognize the United Nations exemption from such taxes, duties or charges, the Contractor shall immediately consult with UNDP to determine a mutually acceptable procedure.

  - Accordingly, the Contractor authorizes UNDP to deduct from the Contractor's invoice any amount representing such taxes, duties or charges, unless the Contractor has consulted with UNDP before the payment thereof and UNDP has, in each instance, specifically authorized the Contractor to pay such taxes, duties or charges under protest. In that event, the Contractor shall provide UNDP with written evidence that payment of such taxes, duties or charges has been made and appropriately authorized.

- CHILD LABOUR

- The Contractor represents and warrants that neither it, nor any of its suppliers is engaged in any practice inconsistent with the rights set forth in the Convention on the Rights of the Child, including Article 32 thereof, which, inter alia, requires that a child shall be protected from performing any work that is likely to be hazardous or to interfere with the child's education, or to be harmful to the child's health or physical mental, spiritual, moral or social development.

- Any breach of this representation and warranty shall entitle UNDP to terminate this Contract immediately upon    notice to the Contractor, at no cost to UNDP.

20. MINES

- The Contractor represents and warrants that neither it nor any of its suppliers is actively and directly engaged in patent activities, development, assembly, production, trade or manufacture of mines or in such activities in respect of components primarily utilized in the manufacture of Mines. The term "Mines" means those devices defined in Article 2, Paragraphs 1, 4 and 5 of Protocol II annexed to the Convention on Prohibitions and Restrictions on the Use of Certain Conventional Weapons Which May Be Deemed to Be Excessively Injurious or to Have Indiscriminate Effects of 1980.

- Any breach of this representation and warranty shall entitle UNDP to terminate this Contract immediately upon notice to the Contractor, without any liability for termination charges or any other liability of any kind of UNDP.

21. OBSERVANCE OF THE LAW

The Contractor shall comply with all laws, ordinances, rules, and regulations bearing upon the performance of its obligations under the terms of this Contract.

22. AUTHORITY TO MODIFY

No modification or change in this Contract, no waiver of any of its provisions or any additional contractual relationship of any kind with the Contractor shall be valid and enforceable against UNDP unless provided by an amendment to this Contract signed by the authorized official of UNDP.